## Sheet1
Period	Month	Week #	Date	Objectives	Tasks
Spring	April	-1	04/13/15	West Coast Research – Figure out what to test next week (test biggest problems faced)
		0	04/20/15	West Coast Research – Figure out what to test next week (test biggest problems faced)
		1	04/27/15	West Coast Research – Figure out what to test next week (test biggest problems faced)
		2	05/04/15	East Coast Research – Figure out what to test next week (test biggest problems faced)
	May	3	05/11/15	East Coast Research – Figure out what to test next week (test biggest problems faced)
		4	05/18/15	East Coast Research – Figure out what to test next week (test biggest problems faced)
		5	05/25/15	East Coast Research – Figure out what to test next week (test biggest problems faced)	1	2
Summer		6	06/01/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	2	4
	June	7	06/08/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	3	6
		8	06/15/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	4	8
		9	06/22/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	5	10
		10	06/29/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	6	12
	July	11	07/06/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	7	14
		12	07/13/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	8	16
		13	07/20/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	9	18
		14	07/27/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	10	20
	August	15	08/03/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	11	22
		16	08/10/15	Build Case Studies (basically get club organizers to each write club in a box), perhaps fill out preliminary sections + Meetups + Tooling + Simulate Clubs in Once A Week Workshops (Monday workshop series, Tuesday workshop series), and have other club organizers test it out as well (like amy), Summer School . Full Year Students?	12	24
Fall		17	08/17/15		1
		18	08/24/15		2
		19	08/31/15		3
	September	20	09/07/15		4
		21	09/14/15		5
		22	09/21/15		6
		23	09/28/15		7
	October	24	10/05/15		8
		25	10/12/15		9
		26	10/19/15		10
		27	10/26/15		11
	November	28	11/02/15		12
		29	11/09/15		13
		30	11/16/15		14
		31	11/23/15		15
	December	32	11/30/15		16
Spring		33	12/07/15		17
		34	12/14/15		18
		35	12/21/15
		36	12/28/15
	January	37	01/04/16
		38	01/11/16
		39	01/18/16
		40	01/25/16
	February	41	02/01/16
		42	02/08/16
		43	02/15/16
		44	02/22/16
		45	02/29/16
	March	46	03/07/16
		47	03/14/16
		48	03/21/16
		49	03/28/16
	April	50	04/04/16
		51	04/11/16
		52	04/18/16
		53	04/25/16
	May	54	05/02/16
		55	05/09/16
		56	05/16/16
		57	05/23/16
		58	05/30/16
Summer	June	59	06/06/16
		60	06/13/16
		61	06/20/16
		62	06/27/16
	July	63	07/04/16
		64	07/11/16
		65	07/18/16
		66	07/25/16
	August	67	08/01/16
		68	08/08/16
		69	08/15/16
Fall		70	08/22/16
		71	08/29/16
	September	72	09/05/16
		73	09/12/16
		74	09/19/16
		75	09/26/16

	December

## Sheet2
A1	B1	C1	D1	E1		A1
A2	B2	C2	D2	E2		A2	B1
A3	B3	C3	D3	E3		A3	B2	C1
A4	B4	C4	D4	E4		A4	B3	C2	D1
A5	B5	C5	D5	E5		A5	B4	C3	D2	E1
A6	B6	C6	D6	E6		A6	B5	C4	D3	E2
A7	B7	C7	D7	E7		A7	B6	C5	D4	E3
A8	B8	C8	D8	E8		A8	B7	C6	D5	E4
A9	B9	C9	D9	E9		A9	B8	C7	D6	E5
A10	B10	C10	D10	E10		A10	B9	C8	D7	E6
A11	B11	C11	D11	E11		A11	B10	C9	D8	E7
A12	B12	C12	D12	E12		A12	B11	C10	D9	E8